## Test Cases
BIBAESTORE — QA TEST TRACKER
Project: BibaeStore E-Commerce ¦ Generated: February 16, 2026 ¦ Version: 1.0
TC-ID | Module | Sub-Module | Test Case | Type | Priority | Status | Tested By | Date Tested | Environment | Notes / Comments | Steps to Reproduce
MODULE: AUTHENTICATION
TC-001 | Authentication | Sign Up | Sign up with valid email, password, full name, and phone | Functional | High | Pending |  |  | Staging
TC-002 | Authentication | Sign Up | Verify password and confirm password match validation | Validation | High | Pending |  |  | Staging
TC-003 | Authentication | Sign Up | Verify required field validation (empty fields) | Validation | High | Pending |  |  | Staging
TC-004 | Authentication | Sign Up | Verify email format validation | Validation | Medium | Pending |  |  | Staging
TC-005 | Authentication | Sign Up | Verify profile image upload during sign up (optional) | Functional | Medium | Pending |  |  | Staging
TC-006 | Authentication | Sign Up | Verify image preview after selecting profile photo | UI | Low | Pending |  |  | Staging
TC-007 | Authentication | Sign Up | Verify successful redirect to login page after sign up | Functional | High | Pending |  |  | Staging
TC-008 | Authentication | Sign Up | Verify success toast notification on account creation | UI | Medium | Pending |  |  | Staging
TC-009 | Authentication | Sign Up | Verify duplicate email shows appropriate error | Validation | High | Pending |  |  | Staging
TC-010 | Authentication | Login | Login with valid email and password | Functional | Critical | Pending |  |  | Staging
TC-011 | Authentication | Login | Verify error message for invalid credentials | Validation | High | Pending |  |  | Staging
TC-012 | Authentication | Login | Verify password show/hide toggle works | UI | Low | Pending |  |  | Staging
TC-013 | Authentication | Login | Verify admin user redirected to /admin dashboard | Functional | Critical | Pending |  |  | Staging
TC-014 | Authentication | Login | Verify regular user redirected to home page | Functional | High | Pending |  |  | Staging
TC-015 | Authentication | Login | Verify session persists after page refresh | Functional | High | Pending |  |  | Staging
TC-016 | Authentication | Login | Verify login success toast notification | UI | Medium | Pending |  |  | Staging
TC-017 | Authentication | Google OAuth | Sign in with Google OAuth button | Functional | High | Pending |  |  | Staging
TC-018 | Authentication | Google OAuth | Verify account auto-creation for first-time Google users | Functional | High | Pending |  |  | Staging
TC-019 | Authentication | Google OAuth | Verify OAuth callback handles redirect properly | Functional | High | Pending |  |  | Staging
TC-020 | Authentication | Google OAuth | Verify session established after Google login | Functional | High | Pending |  |  | Staging
TC-021 | Authentication | Logout | Verify user can log out successfully | Functional | High | Pending |  |  | Staging
TC-022 | Authentication | Logout | Verify session cleared after logout | Security | High | Pending |  |  | Staging
TC-023 | Authentication | Logout | Verify redirect to home page after logout | Functional | Medium | Pending |  |  | Staging
TC-024 | Authentication | Protected Routes | Verify /profile redirects to /login if unauthenticated | Security | Critical | Pending |  |  | Staging
TC-025 | Authentication | Protected Routes | Verify /admin requires admin email to access | Security | Critical | Pending |  |  | Staging
TC-026 | Authentication | Protected Routes | Verify /login and /signup redirect logged-in users to home | Functional | Medium | Pending |  |  | Staging
TC-027 | Authentication | Protected Routes | Verify return URL preserved after login redirect | Functional | Medium | Pending |  |  | Staging
MODULE: HOMEPAGE
TC-028 | Homepage | Hero Section | Verify hero section displays with CTA button | UI | High | Pending |  |  | Staging
TC-029 | Homepage | Hero Section | Verify hero section responsive on mobile | Responsive | Medium | Pending |  |  | Staging
TC-030 | Homepage | Sections | Verify Trust Badges section renders | UI | Medium | Pending |  |  | Staging
TC-031 | Homepage | Sections | Verify Category Highlights loads categories | Functional | High | Pending |  |  | Staging
TC-032 | Homepage | Sections | Verify Featured Products shows is_featured products (max 8) | Functional | High | Pending |  |  | Staging
TC-033 | Homepage | Sections | Verify New Arrivals shows latest 8 products | Functional | High | Pending |  |  | Staging
TC-034 | Homepage | Sections | Verify Testimonials section renders | UI | Medium | Pending |  |  | Staging
TC-035 | Homepage | Sections | Verify Newsletter signup form works | Functional | Medium | Pending |  |  | Staging
TC-036 | Homepage | Sections | Verify all products fetched fresh from backend (no cache) | Performance | Critical | Pending |  |  | Staging
MODULE: SHOP
TC-037 | Shop | Product Display | Verify all products load from Supabase on page visit | Functional | Critical | Pending |  |  | Staging
TC-038 | Shop | Product Display | Verify products display with image, name, price | UI | High | Pending |  |  | Staging
TC-039 | Shop | Product Display | Verify sale price shows with original price strikethrough | UI | Medium | Pending |  |  | Staging
TC-040 | Shop | Product Display | Verify product count displayed in header | UI | Low | Pending |  |  | Staging
TC-041 | Shop | Product Display | Verify page always shows fresh data (no cache) | Performance | Critical | Pending |  |  | Staging
TC-042 | Shop | Search & Filter | Search products by name (case-insensitive) | Functional | High | Pending |  |  | Staging
TC-043 | Shop | Search & Filter | Filter products by category from URL param (?category=Ladies) | Functional | High | Pending |  |  | Staging
TC-044 | Shop | Search & Filter | Filter products by category from filter panel | Functional | High | Pending |  |  | Staging
TC-045 | Shop | Search & Filter | Verify category filter shows product count per category | UI | Medium | Pending |  |  | Staging
TC-046 | Shop | Search & Filter | Clear category filter shows all products | Functional | Medium | Pending |  |  | Staging
TC-047 | Shop | Search & Filter | Verify combined search + category filter works | Functional | Medium | Pending |  |  | Staging
TC-048 | Shop | Sorting | Sort by Price: Low to High | Functional | Medium | Pending |  |  | Staging
TC-049 | Shop | Sorting | Sort by Price: High to Low | Functional | Medium | Pending |  |  | Staging
TC-050 | Shop | Sorting | Sort by Newest First | Functional | Medium | Pending |  |  | Staging
TC-051 | Shop | Sorting | Sort by Top Rated | Functional | Medium | Pending |  |  | Staging
TC-052 | Shop | Sorting | Reset sort to default | Functional | Low | Pending |  |  | Staging
TC-053 | Shop | Grid & UI | Toggle grid layout to 3 columns | UI | Low | Pending |  |  | Staging
TC-054 | Shop | Grid & UI | Toggle grid layout to 4 columns | UI | Low | Pending |  |  | Staging
TC-055 | Shop | Grid & UI | Verify filters panel expand/collapse animation | UI | Low | Pending |  |  | Staging
TC-056 | Shop | Grid & UI | Verify skeleton loader during filtering | UI | Low | Pending |  |  | Staging
TC-057 | Shop | Grid & UI | Verify empty state when no products match filter | UI | Medium | Pending |  |  | Staging
TC-058 | Shop | Grid & UI | Verify responsive layout on mobile (2 columns) | Responsive | Medium | Pending |  |  | Staging
TC-059 | Shop | Real-time Updates | Products auto-update when admin creates a new product | Functional | High | Pending |  |  | Staging
TC-060 | Shop | Real-time Updates | Products auto-update when admin edits a product | Functional | High | Pending |  |  | Staging
TC-061 | Shop | Real-time Updates | Products auto-update when admin deletes a product | Functional | High | Pending |  |  | Staging
TC-062 | Shop | Real-time Updates | Verify toast notification on real-time product update | UI | Medium | Pending |  |  | Staging
MODULE: PRODUCT DETAIL
TC-063 | Product Detail | Display | Verify product name, price, description display correctly | UI | High | Pending |  |  | Staging
TC-064 | Product Detail | Display | Verify sale price shows with strikethrough original | UI | Medium | Pending |  |  | Staging
TC-065 | Product Detail | Display | Verify multiple product images / image carousel | UI | High | Pending |  |  | Staging
TC-066 | Product Detail | Display | Verify short description and full description | UI | Medium | Pending |  |  | Staging
TC-067 | Product Detail | Display | Verify stock availability indicator | UI | Medium | Pending |  |  | Staging
TC-068 | Product Detail | Display | Verify product page returns 404 for non-existent ID | Functional | High | Pending |  |  | Staging
TC-069 | Product Detail | Display | Verify data fetched fresh from backend (no cache) | Performance | High | Pending |  |  | Staging
TC-070 | Product Detail | Actions | Add product to cart with selected size and color | Functional | Critical | Pending |  |  | Staging
TC-071 | Product Detail | Actions | Add product to wishlist (heart icon) | Functional | High | Pending |  |  | Staging
TC-072 | Product Detail | Actions | Remove product from wishlist (toggle) | Functional | Medium | Pending |  |  | Staging
TC-073 | Product Detail | Actions | Verify size/color selection required before add to cart | Validation | High | Pending |  |  | Staging
TC-074 | Product Detail | Related Products | Verify related products from same category display | Functional | Medium | Pending |  |  | Staging
TC-075 | Product Detail | Related Products | Verify max 4 related products shown | UI | Low | Pending |  |  | Staging
TC-076 | Product Detail | Related Products | Verify clicking related product navigates to its page | Functional | Medium | Pending |  |  | Staging
TC-077 | Product Detail | Reviews | Verify product reviews display with star ratings | UI | Medium | Pending |  |  | Staging
TC-078 | Product Detail | Reviews | Verify reviewer name and profile image shown | UI | Low | Pending |  |  | Staging
TC-079 | Product Detail | Reviews | Verify reviews ordered by newest first | Functional | Low | Pending |  |  | Staging
MODULE: CART
TC-080 | Cart | Cart Operations | Add product to cart from product detail page | Functional | Critical | Pending |  |  | Staging
TC-081 | Cart | Cart Operations | Verify cart item shows image, name, price, size, color | UI | High | Pending |  |  | Staging
TC-082 | Cart | Cart Operations | Increase item quantity using + button | Functional | High | Pending |  |  | Staging
TC-083 | Cart | Cart Operations | Decrease item quantity using - button | Functional | High | Pending |  |  | Staging
TC-084 | Cart | Cart Operations | Remove item from cart with delete button | Functional | High | Pending |  |  | Staging
TC-085 | Cart | Cart Operations | Verify confirmation dialog on item removal | UI | Medium | Pending |  |  | Staging
TC-086 | Cart | Cart Operations | Verify cart empties and shows empty state message | UI | Medium | Pending |  |  | Staging
TC-087 | Cart | Cart Operations | Verify 'Continue Shopping' link returns to shop | Functional | Low | Pending |  |  | Staging
TC-088 | Cart | Calculations | Verify subtotal calculates correctly | Functional | Critical | Pending |  |  | Staging
TC-089 | Cart | Calculations | Verify shipping cost displays (PKR 200) | Functional | High | Pending |  |  | Staging
TC-090 | Cart | Calculations | Verify total = subtotal + shipping | Functional | Critical | Pending |  |  | Staging
TC-091 | Cart | Calculations | Verify totals update when quantity changes | Functional | High | Pending |  |  | Staging
TC-092 | Cart | Persistence | Guest cart persists in localStorage on page refresh | Functional | Critical | Pending |  |  | Staging
TC-093 | Cart | Persistence | Logged-in user cart persists in database | Functional | Critical | Pending |  |  | Staging
TC-094 | Cart | Persistence | Guest cart merges with database cart on login | Functional | High | Pending |  |  | Staging
TC-095 | Cart | Persistence | Cart survives browser tab close and reopen | Functional | Medium | Pending |  |  | Staging
MODULE: CHECKOUT
TC-096 | Checkout | Step 1: Contact Info | Verify email field required validation | Validation | High | Pending |  |  | Staging
TC-097 | Checkout | Step 1: Contact Info | Verify phone field required validation | Validation | High | Pending |  |  | Staging
TC-098 | Checkout | Step 1: Contact Info | Verify email format validation | Validation | Medium | Pending |  |  | Staging
TC-099 | Checkout | Step 1: Contact Info | Verify guest checkout allowed without login | Functional | High | Pending |  |  | Staging
TC-100 | Checkout | Step 1: Contact Info | Verify login modal option to auto-fill from profile | Functional | Medium | Pending |  |  | Staging
TC-101 | Checkout | Step 1: Contact Info | Navigate to Step 2 after valid contact info | Functional | High | Pending |  |  | Staging
TC-102 | Checkout | Step 2: Shipping | Verify first name, last name required | Validation | High | Pending |  |  | Staging
TC-103 | Checkout | Step 2: Shipping | Verify address, city, state, postal code required | Validation | High | Pending |  |  | Staging
TC-104 | Checkout | Step 2: Shipping | Verify country dropdown with all options (PK, IN, BD, AE, UK, US) | Functional | Medium | Pending |  |  | Staging
TC-105 | Checkout | Step 2: Shipping | Verify profile auto-fill for logged-in users | Functional | Medium | Pending |  |  | Staging
TC-106 | Checkout | Step 2: Shipping | Navigate back to Step 1 | Functional | Low | Pending |  |  | Staging
TC-107 | Checkout | Step 2: Shipping | Navigate to Step 3 after valid shipping info | Functional | High | Pending |  |  | Staging
TC-108 | Checkout | Step 3: Payment | Select Cash on Delivery (COD) payment method | Functional | High | Pending |  |  | Staging
TC-109 | Checkout | Step 3: Payment | Select Bank Transfer payment method | Functional | High | Pending |  |  | Staging
TC-110 | Checkout | Step 3: Payment | Verify bank options display (Sadapay, JazzCash, Easypaisa, Askari) | UI | Medium | Pending |  |  | Staging
TC-111 | Checkout | Step 3: Payment | Verify account numbers display for selected bank | UI | Medium | Pending |  |  | Staging
TC-112 | Checkout | Step 3: Payment | Upload payment proof image (JPG/PNG) | Functional | Critical | Pending |  |  | Staging
TC-113 | Checkout | Step 3: Payment | Verify file size validation (max 5MB) | Validation | High | Pending |  |  | Staging
TC-114 | Checkout | Step 3: Payment | Verify drag-and-drop file upload works | Functional | Medium | Pending |  |  | Staging
TC-115 | Checkout | Step 3: Payment | Navigate to Step 4 after valid payment info | Functional | High | Pending |  |  | Staging
TC-116 | Checkout | Step 4: Review & Place Order | Verify all entered data displayed in review | Functional | High | Pending |  |  | Staging
TC-117 | Checkout | Step 4: Review & Place Order | Verify order items list with quantities and totals | UI | High | Pending |  |  | Staging
TC-118 | Checkout | Step 4: Review & Place Order | Verify final price calculation correct | Functional | Critical | Pending |  |  | Staging
TC-119 | Checkout | Step 4: Review & Place Order | Place order successfully | Functional | Critical | Pending |  |  | Staging
TC-120 | Checkout | Step 4: Review & Place Order | Verify tracking number generated | Functional | Critical | Pending |  |  | Staging
TC-121 | Checkout | Step 4: Review & Place Order | Verify confirmation email sent to customer | Functional | High | Pending |  |  | Staging
TC-122 | Checkout | Step 4: Review & Place Order | Verify redirect to success page | Functional | High | Pending |  |  | Staging
TC-123 | Checkout | Step 4: Review & Place Order | Verify cart cleared after order placement | Functional | High | Pending |  |  | Staging
TC-124 | Checkout | Progress & UI | Verify step progress indicator shows completed steps | UI | Medium | Pending |  |  | Staging
TC-125 | Checkout | Progress & UI | Verify back navigation between steps preserves data | Functional | High | Pending |  |  | Staging
TC-126 | Checkout | Progress & UI | Verify order summary sidebar updates in real-time | UI | Medium | Pending |  |  | Staging
TC-127 | Checkout | Progress & UI | Verify empty cart redirect if no items | Functional | Medium | Pending |  |  | Staging
TC-128 | Checkout | Progress & UI | Verify responsive layout (mobile vs desktop) | Responsive | Medium | Pending |  |  | Staging
MODULE: CHECKOUT SUCCESS
TC-129 | Checkout Success | Display | Verify confetti animation on page load | UI | Low | Pending |  |  | Staging
TC-130 | Checkout Success | Display | Verify tracking number displayed | Functional | High | Pending |  |  | Staging
TC-131 | Checkout Success | Display | Verify copy-to-clipboard button for tracking number | Functional | Medium | Pending |  |  | Staging
TC-132 | Checkout Success | Display | Verify order total displayed correctly | Functional | High | Pending |  |  | Staging
TC-133 | Checkout Success | Display | Verify COD: shows 'Order Confirmed' state | Functional | Medium | Pending |  |  | Staging
TC-134 | Checkout Success | Display | Verify Bank Transfer: shows 'Order Under Review' state | Functional | Medium | Pending |  |  | Staging
TC-135 | Checkout Success | Display | Verify status timeline showing order progression | UI | Medium | Pending |  |  | Staging
TC-136 | Checkout Success | Display | Verify WhatsApp contact button works | Functional | Low | Pending |  |  | Staging
TC-137 | Checkout Success | Display | Verify 'Continue Shopping' link navigates to shop | Functional | Low | Pending |  |  | Staging
TC-138 | Checkout Success | Display | Verify 'Track Order' link pre-filled with tracking number | Functional | Medium | Pending |  |  | Staging
MODULE: ORDER TRACKING
TC-139 | Order Tracking | Search | Search order by tracking number | Functional | Critical | Pending |  |  | Staging
TC-140 | Order Tracking | Search | Verify order not found message for invalid tracking | Functional | High | Pending |  |  | Staging
TC-141 | Order Tracking | Search | Verify auto-populate from success page link | Functional | Medium | Pending |  |  | Staging
TC-142 | Order Tracking | Timeline | Verify order timeline displays all statuses | UI | High | Pending |  |  | Staging
TC-143 | Order Tracking | Timeline | Verify each status shows timestamp | UI | Medium | Pending |  |  | Staging
TC-144 | Order Tracking | Timeline | Verify relative time display (e.g., '2 hours ago') | UI | Low | Pending |  |  | Staging
TC-145 | Order Tracking | Timeline | Verify cancelled order shows alert state | Functional | Medium | Pending |  |  | Staging
TC-146 | Order Tracking | Timeline | Verify WhatsApp support link | UI | Low | Pending |  |  | Staging
TC-147 | Order Tracking | Timeline | Verify responsive timeline on mobile | Responsive | Medium | Pending |  |  | Staging
MODULE: WISHLIST
TC-148 | Wishlist | Operations | Add product to wishlist from product card | Functional | High | Pending |  |  | Staging
TC-149 | Wishlist | Operations | Add product to wishlist from product detail page | Functional | High | Pending |  |  | Staging
TC-150 | Wishlist | Operations | Remove product from wishlist | Functional | High | Pending |  |  | Staging
TC-151 | Wishlist | Operations | Toggle wishlist (add/remove on same click) | Functional | Medium | Pending |  |  | Staging
TC-152 | Wishlist | Operations | Verify wishlist count updates in header/icon | UI | Medium | Pending |  |  | Staging
TC-153 | Wishlist | Page | Verify wishlist page displays all saved items | Functional | High | Pending |  |  | Staging
TC-154 | Wishlist | Page | Verify remove button on each wishlist item | Functional | Medium | Pending |  |  | Staging
TC-155 | Wishlist | Page | Verify empty wishlist message with shop link | UI | Medium | Pending |  |  | Staging
TC-156 | Wishlist | Page | Verify wishlist persists on page refresh (localStorage) | Functional | High | Pending |  |  | Staging
TC-157 | Wishlist | Page | Verify responsive grid layout | Responsive | Low | Pending |  |  | Staging
MODULE: USER PROFILE
TC-158 | User Profile | Profile | View user profile information (name, email, phone) | Functional | High | Pending |  |  | Staging
TC-159 | User Profile | Profile | Edit profile information | Functional | High | Pending |  |  | Staging
TC-160 | User Profile | Profile | Upload/change profile picture | Functional | Medium | Pending |  |  | Staging
TC-161 | User Profile | Profile | Verify logout button works | Functional | High | Pending |  |  | Staging
TC-162 | User Profile | My Orders | View list of all user orders | Functional | High | Pending |  |  | Staging
TC-163 | User Profile | My Orders | Verify order displays tracking #, date, amount, status | UI | High | Pending |  |  | Staging
TC-164 | User Profile | My Orders | Expand order to see full details | Functional | Medium | Pending |  |  | Staging
TC-165 | User Profile | My Orders | Verify order items list with images and prices | UI | Medium | Pending |  |  | Staging
TC-166 | User Profile | My Orders | Copy tracking number button works | Functional | Medium | Pending |  |  | Staging
TC-167 | User Profile | My Orders | Track order button navigates to tracking page | Functional | Medium | Pending |  |  | Staging
TC-168 | User Profile | My Orders | Request cancellation for pending/under_review orders | Functional | High | Pending |  |  | Staging
TC-169 | User Profile | My Orders | Verify cancellation form with reason textarea | Functional | Medium | Pending |  |  | Staging
TC-170 | User Profile | My Orders | Verify empty state if no orders | UI | Low | Pending |  |  | Staging
TC-171 | User Profile | My Orders | Verify mobile card layout vs desktop table | Responsive | Medium | Pending |  |  | Staging
MODULE: ADMIN DASHBOARD
TC-172 | Admin Dashboard | KPI Cards | Verify Total Revenue card with today's amount | Functional | High | Pending |  |  | Staging
TC-173 | Admin Dashboard | KPI Cards | Verify Active Orders card with today's count | Functional | High | Pending |  |  | Staging
TC-174 | Admin Dashboard | KPI Cards | Verify Total Customers count | Functional | High | Pending |  |  | Staging
TC-175 | Admin Dashboard | KPI Cards | Verify Average Order Value calculation | Functional | Medium | Pending |  |  | Staging
TC-176 | Admin Dashboard | Live Data | Verify latest 5 orders table loads | Functional | High | Pending |  |  | Staging
TC-177 | Admin Dashboard | Live Data | Verify order rows show tracking #, customer, date, total, status | UI | Medium | Pending |  |  | Staging
TC-178 | Admin Dashboard | Live Data | Verify payment method badge (Bank/COD) | UI | Low | Pending |  |  | Staging
TC-179 | Admin Dashboard | Live Data | Verify order status badge with correct color | UI | Low | Pending |  |  | Staging
TC-180 | Admin Dashboard | Live Data | Verify order summary panel with status distribution | Functional | Medium | Pending |  |  | Staging
TC-181 | Admin Dashboard | Live Data | Verify bar charts with animated widths | UI | Low | Pending |  |  | Staging
TC-182 | Admin Dashboard | Notifications | Verify new order notification banner appears | Functional | High | Pending |  |  | Staging
TC-183 | Admin Dashboard | Notifications | Verify notification count increments in real-time | Functional | High | Pending |  |  | Staging
TC-184 | Admin Dashboard | Notifications | Verify real-time stats refresh on new orders | Functional | High | Pending |  |  | Staging
TC-185 | Admin Dashboard | Notifications | Verify 'View All Orders' button navigates | Functional | Low | Pending |  |  | Staging
TC-186 | Admin Dashboard | Notifications | Verify 'Create Product' button navigates | Functional | Low | Pending |  |  | Staging
MODULE: ADMIN PRODUCTS
TC-187 | Admin Products | List | Verify product list table loads with all columns | Functional | High | Pending |  |  | Staging
TC-188 | Admin Products | List | Verify product image thumbnail displayed | UI | Medium | Pending |  |  | Staging
TC-189 | Admin Products | List | Verify pagination (20 products per page) | Functional | Medium | Pending |  |  | Staging
TC-190 | Admin Products | List | Verify mobile card view alternative | Responsive | Medium | Pending |  |  | Staging
TC-191 | Admin Products | Create | Open 'Add Product' form modal | Functional | High | Pending |  |  | Staging
TC-192 | Admin Products | Create | Fill and submit product with all required fields | Functional | Critical | Pending |  |  | Staging
TC-193 | Admin Products | Create | Upload multiple product images | Functional | High | Pending |  |  | Staging
TC-194 | Admin Products | Create | Verify drag-and-drop image upload | Functional | Medium | Pending |  |  | Staging
TC-195 | Admin Products | Create | Verify SKU uniqueness validation | Validation | High | Pending |  |  | Staging
TC-196 | Admin Products | Create | Verify category dropdown selection | Functional | Medium | Pending |  |  | Staging
TC-197 | Admin Products | Create | Set product as featured (toggle) | Functional | Medium | Pending |  |  | Staging
TC-198 | Admin Products | Create | Set product status (active/draft/inactive) | Functional | Medium | Pending |  |  | Staging
TC-199 | Admin Products | Create | Verify product appears in list after creation | Functional | High | Pending |  |  | Staging
TC-200 | Admin Products | Edit | Click edit icon opens pre-filled product form | Functional | High | Pending |  |  | Staging
TC-201 | Admin Products | Edit | Update product name and verify saved | Functional | High | Pending |  |  | Staging
TC-202 | Admin Products | Edit | Update price/sale price and verify | Functional | High | Pending |  |  | Staging
TC-203 | Admin Products | Edit | Add/remove product images | Functional | Medium | Pending |  |  | Staging
TC-204 | Admin Products | Edit | Change category and verify | Functional | Medium | Pending |  |  | Staging
TC-205 | Admin Products | Edit | Toggle featured status | Functional | Medium | Pending |  |  | Staging
TC-206 | Admin Products | Edit | Verify updated product reflects on shop page | Functional | Critical | Pending |  |  | Staging
TC-207 | Admin Products | Delete | Click delete icon shows confirmation dialog | UI | High | Pending |  |  | Staging
TC-208 | Admin Products | Delete | Confirm deletion removes product | Functional | Critical | Pending |  |  | Staging
TC-209 | Admin Products | Delete | Cancel deletion keeps product | Functional | Medium | Pending |  |  | Staging
TC-210 | Admin Products | Delete | Verify deleted product removed from shop page | Functional | High | Pending |  |  | Staging
TC-211 | Admin Products | View Details | Click view icon opens product detail modal | Functional | Medium | Pending |  |  | Staging
TC-212 | Admin Products | View Details | Verify all product images in carousel | UI | Medium | Pending |  |  | Staging
TC-213 | Admin Products | View Details | Verify product info (name, SKU, price, stock, category, status) | UI | Medium | Pending |  |  | Staging
MODULE: ADMIN CATEGORIES
TC-214 | Admin Categories | List | Verify categories list loads with all columns | Functional | High | Pending |  |  | Staging
TC-215 | Admin Categories | List | Verify category image thumbnail | UI | Low | Pending |  |  | Staging
TC-216 | Admin Categories | List | Verify type badge (Main/Subcategory) | UI | Low | Pending |  |  | Staging
TC-217 | Admin Categories | List | Verify mobile card view | Responsive | Medium | Pending |  |  | Staging
TC-218 | Admin Categories | CRUD | Create new main category with name and image | Functional | High | Pending |  |  | Staging
TC-219 | Admin Categories | CRUD | Create subcategory with parent category selected | Functional | High | Pending |  |  | Staging
TC-220 | Admin Categories | CRUD | Edit category name and image | Functional | High | Pending |  |  | Staging
TC-221 | Admin Categories | CRUD | Delete category with confirmation | Functional | High | Pending |  |  | Staging
TC-222 | Admin Categories | CRUD | Verify sort order management | Functional | Medium | Pending |  |  | Staging
TC-223 | Admin Categories | CRUD | Verify status toggle (active/inactive) | Functional | Medium | Pending |  |  | Staging
MODULE: ADMIN ORDERS
TC-224 | Admin Orders | List & Search | Verify orders list loads with all columns | Functional | High | Pending |  |  | Staging
TC-225 | Admin Orders | List & Search | Search orders by tracking number | Functional | High | Pending |  |  | Staging
TC-226 | Admin Orders | List & Search | Search orders by customer name | Functional | Medium | Pending |  |  | Staging
TC-227 | Admin Orders | List & Search | Filter orders by status (Pending, Processing, etc.) | Functional | High | Pending |  |  | Staging
TC-228 | Admin Orders | List & Search | Verify real-time new order appears at top | Functional | Critical | Pending |  |  | Staging
TC-229 | Admin Orders | List & Search | Verify new order highlight animation (yellow, 3 sec) | UI | Medium | Pending |  |  | Staging
TC-230 | Admin Orders | List & Search | Verify notification count updates | Functional | High | Pending |  |  | Staging
TC-231 | Admin Orders | Order Detail Modal | Open order detail modal by clicking tracking # | Functional | High | Pending |  |  | Staging
TC-232 | Admin Orders | Order Detail Modal | Verify customer info with guest badge if applicable | UI | Medium | Pending |  |  | Staging
TC-233 | Admin Orders | Order Detail Modal | Verify shipping address displayed | UI | Medium | Pending |  |  | Staging
TC-234 | Admin Orders | Order Detail Modal | Verify tracking number displayed | UI | Medium | Pending |  |  | Staging
TC-235 | Admin Orders | Order Detail Modal | Verify payment method and status | UI | Medium | Pending |  |  | Staging
TC-236 | Admin Orders | Order Detail Modal | Verify payment proof image loads (bank transfer) | Functional | High | Pending |  |  | Staging
TC-237 | Admin Orders | Order Detail Modal | Verify order items list with images and prices | UI | Medium | Pending |  |  | Staging
TC-238 | Admin Orders | Order Detail Modal | Verify order summary with subtotal, shipping, total | Functional | Medium | Pending |  |  | Staging
TC-239 | Admin Orders | Order Detail Modal | Verify status history timeline | UI | Medium | Pending |  |  | Staging
TC-240 | Admin Orders | Order Detail Modal | Save admin notes | Functional | Medium | Pending |  |  | Staging
TC-241 | Admin Orders | Status Actions | Confirm order (pending → confirmed) | Functional | Critical | Pending |  |  | Staging
TC-242 | Admin Orders | Status Actions | Mark order as Processing | Functional | High | Pending |  |  | Staging
TC-243 | Admin Orders | Status Actions | Mark order as Shipped (dispatch dialog) | Functional | Critical | Pending |  |  | Staging
TC-244 | Admin Orders | Status Actions | Verify dispatch note input before shipping | Functional | Medium | Pending |  |  | Staging
TC-245 | Admin Orders | Status Actions | Mark order as Delivered | Functional | Critical | Pending |  |  | Staging
TC-246 | Admin Orders | Status Actions | Cancel order from admin | Functional | High | Pending |  |  | Staging
TC-247 | Admin Orders | Status Actions | Approve customer cancellation request | Functional | High | Pending |  |  | Staging
TC-248 | Admin Orders | Status Actions | Reject customer cancellation request | Functional | Medium | Pending |  |  | Staging
TC-249 | Admin Orders | Payment Actions | Verify payment button for bank transfer orders | Functional | Critical | Pending |  |  | Staging
TC-250 | Admin Orders | Payment Actions | Reject payment (with reason) | Functional | High | Pending |  |  | Staging
TC-251 | Admin Orders | Payment Actions | Verify payment status badge updates | UI | Medium | Pending |  |  | Staging
TC-252 | Admin Orders | Print & Export | Print shipping label with correct layout | Functional | High | Pending |  |  | Staging
TC-253 | Admin Orders | Print & Export | Verify shipping label has tracking #, customer info, items | UI | Medium | Pending |  |  | Staging
TC-254 | Admin Orders | Print & Export | Export filtered orders as CSV | Functional | High | Pending |  |  | Staging
TC-255 | Admin Orders | Print & Export | Verify CSV contains all order data | Functional | Medium | Pending |  |  | Staging
MODULE: EMAIL
TC-256 | Email | Transactional Emails | Order confirmation email sent after placement | Functional | Critical | Pending |  |  | Staging
TC-257 | Email | Transactional Emails | Payment verified email sent (bank transfer) | Functional | High | Pending |  |  | Staging
TC-258 | Email | Transactional Emails | Order shipped / dispatched email sent | Functional | High | Pending |  |  | Staging
TC-259 | Email | Transactional Emails | Order delivered email sent | Functional | Medium | Pending |  |  | Staging
TC-260 | Email | Transactional Emails | Cancellation approved email sent | Functional | Medium | Pending |  |  | Staging
TC-261 | Email | Transactional Emails | Payment rejected email sent | Functional | Medium | Pending |  |  | Staging
TC-262 | Email | Transactional Emails | Verify email contains correct order data | Functional | High | Pending |  |  | Staging
TC-263 | Email | Transactional Emails | Verify email formatting and branding | UI | Medium | Pending |  |  | Staging
MODULE: NAVIGATION
TC-264 | Navigation | Header | Verify header shows logo, nav links, cart icon, user menu | UI | High | Pending |  |  | Staging
TC-265 | Navigation | Header | Verify cart icon shows item count badge | UI | Medium | Pending |  |  | Staging
TC-266 | Navigation | Header | Verify user menu dropdown (login/profile/logout) | Functional | Medium | Pending |  |  | Staging
TC-267 | Navigation | Header | Verify mobile hamburger menu | Responsive | High | Pending |  |  | Staging
TC-268 | Navigation | Header | Verify header sticky on scroll | UI | Low | Pending |  |  | Staging
TC-269 | Navigation | Footer | Verify footer displays links and contact info | UI | Medium | Pending |  |  | Staging
TC-270 | Navigation | Footer | Verify social media links | UI | Low | Pending |  |  | Staging
TC-271 | Navigation | Footer | Verify footer responsive layout | Responsive | Low | Pending |  |  | Staging
TC-272 | Navigation | Page Transitions | Verify smooth page transition animations | UI | Low | Pending |  |  | Staging
TC-273 | Navigation | Page Transitions | Verify top loading bar during navigation | UI | Low | Pending |  |  | Staging
TC-274 | Navigation | Page Transitions | Verify 404 page displays for invalid routes | Functional | Medium | Pending |  |  | Staging
MODULE: PERFORMANCE
TC-275 | Performance | Caching | Verify NO server-side cache on home page (force-dynamic) | Performance | Critical | Pending |  |  | Staging
TC-276 | Performance | Caching | Verify NO server-side cache on shop page | Performance | Critical | Pending |  |  | Staging
TC-277 | Performance | Caching | Verify NO server-side cache on product detail page | Performance | Critical | Pending |  |  | Staging
TC-278 | Performance | Caching | Verify NO client-side router cache (staleTimes=0) | Performance | High | Pending |  |  | Staging
TC-279 | Performance | Caching | Verify Cache-Control: no-store headers in responses | Performance | High | Pending |  |  | Staging
TC-280 | Performance | Loading | Verify page load time acceptable (< 5 seconds) | Performance | High | Pending |  |  | Staging
TC-281 | Performance | Loading | Verify images load properly with Next.js optimization | Performance | Medium | Pending |  |  | Staging
TC-282 | Performance | Loading | Verify animations smooth at 60fps | Performance | Low | Pending |  |  | Staging
TC-283 | Performance | Loading | Verify no console errors in browser | Performance | High | Pending |  |  | Staging
TC-284 | Performance | Loading | Verify no memory leaks on navigation | Performance | Medium | Pending |  |  | Staging
MODULE: SECURITY
TC-285 | Security | Access Control | Verify admin routes blocked for non-admin users | Security | Critical | Pending |  |  | Staging
TC-286 | Security | Access Control | Verify protected routes redirect unauthenticated users | Security | Critical | Pending |  |  | Staging
TC-287 | Security | Access Control | Verify user cannot access another user's order data | Security | Critical | Pending |  |  | Staging
TC-288 | Security | Access Control | Verify password field masked in all forms | Security | High | Pending |  |  | Staging
TC-289 | Security | Access Control | Verify no sensitive data exposed in URLs | Security | High | Pending |  |  | Staging
TC-290 | Security | Access Control | Verify CORS properly configured | Security | Medium | Pending |  |  | Staging
TC-291 | Security | Access Control | Verify input validation on all forms (XSS prevention) | Security | High | Pending |  |  | Staging
MODULE: RESPONSIVE
TC-292 | Responsive | Mobile (375px) | Homepage renders correctly on mobile | Responsive | High | Pending |  |  | Staging
TC-293 | Responsive | Mobile (375px) | Shop page 2-column grid on mobile | Responsive | High | Pending |  |  | Staging
TC-294 | Responsive | Mobile (375px) | Product detail page readable on mobile | Responsive | High | Pending |  |  | Staging
TC-295 | Responsive | Mobile (375px) | Cart page single-column layout on mobile | Responsive | Medium | Pending |  |  | Staging
TC-296 | Responsive | Mobile (375px) | Checkout form usable on mobile | Responsive | High | Pending |  |  | Staging
TC-297 | Responsive | Mobile (375px) | Admin pages accessible on mobile | Responsive | Medium | Pending |  |  | Staging
TC-298 | Responsive | Tablet (768px) | Verify layout adapts at tablet breakpoint | Responsive | Medium | Pending |  |  | Staging
TC-299 | Responsive | Tablet (768px) | Verify navigation adapts | Responsive | Medium | Pending |  |  | Staging
TC-300 | Responsive | Desktop (1024px+) | Verify full desktop layout renders correctly | Responsive | High | Pending |  |  | Staging
TC-301 | Responsive | Desktop (1024px+) | Verify 4-column product grid on desktop | Responsive | Medium | Pending |  |  | Staging
MODULE: EDGE CASES
TC-302 | Edge Cases | Error Handling | Network error shows appropriate message | Functional | High | Pending |  |  | Staging
TC-303 | Edge Cases | Error Handling | Slow network detection and toast notification | Functional | Medium | Pending |  |  | Staging
TC-304 | Edge Cases | Error Handling | Form submission behavior when offline | Functional | Medium | Pending |  |  | Staging
TC-305 | Edge Cases | Error Handling | Session expiration handled gracefully | Functional | High | Pending |  |  | Staging
TC-306 | Edge Cases | Error Handling | Payment proof upload failure handled | Functional | Medium | Pending |  |  | Staging
TC-307 | Edge Cases | Boundary | Add product with 0 stock — verify behavior | Functional | Medium | Pending |  |  | Staging
TC-308 | Edge Cases | Boundary | Access deleted product URL — verify 404 | Functional | Medium | Pending |  |  | Staging
TC-309 | Edge Cases | Boundary | Multiple browser tabs — cart sync behavior | Functional | Medium | Pending |  |  | Staging
TC-310 | Edge Cases | Boundary | Browser back button on checkout — preserves data | Functional | Medium | Pending |  |  | Staging
TC-311 | Edge Cases | Boundary | Extremely long product name — UI handles overflow | UI | Low | Pending |  |  | Staging
TC-312 | Edge Cases | Boundary | Large image upload — verify size limit enforced | Validation | Medium | Pending |  |  | Staging

## Summary Dashboard
QA TEST EXECUTION SUMMARY
Total Test Cases: 312 ¦ Generated: February 16, 2026
Module | Total Tests | Pass | Fail | Pending | Blocked
Authentication | 27 | 0 | 0 | 27 | 0
Homepage | 9 | 0 | 0 | 9 | 0
Shop | 26 | 0 | 0 | 26 | 0
Product Detail | 17 | 0 | 0 | 17 | 0
Cart | 16 | 0 | 0 | 16 | 0
Checkout | 33 | 0 | 0 | 33 | 0
Checkout Success | 10 | 0 | 0 | 10 | 0
Order Tracking | 9 | 0 | 0 | 9 | 0
Wishlist | 10 | 0 | 0 | 10 | 0
User Profile | 14 | 0 | 0 | 14 | 0
Admin Dashboard | 15 | 0 | 0 | 15 | 0
Admin Products | 27 | 0 | 0 | 27 | 0
Admin Categories | 10 | 0 | 0 | 10 | 0
Admin Orders | 32 | 0 | 0 | 32 | 0
Email | 8 | 0 | 0 | 8 | 0
Navigation | 11 | 0 | 0 | 11 | 0
Performance | 10 | 0 | 0 | 10 | 0
Security | 7 | 0 | 0 | 7 | 0
Responsive | 10 | 0 | 0 | 10 | 0
Edge Cases | 11 | 0 | 0 | 11 | 0
TOTAL | 312 | 0 | 0 | 312 | 0
PROGRESS METRICS
Total Executed | 0
Pass Rate | 0
Fail Rate | 0
Completion % | 0

## Defect Log
DEFECT / BUG TRACKING LOG
Bug ID | Related TC | Module | Summary | Severity | Status | Reported By | Date Reported | Assigned To | Resolution Notes
BUG-001
BUG-002
BUG-003
BUG-004
BUG-005
BUG-006
BUG-007
BUG-008
BUG-009
BUG-010
BUG-011
BUG-012
BUG-013
BUG-014
BUG-015
BUG-016
BUG-017
BUG-018
BUG-019
BUG-020
BUG-021
BUG-022
BUG-023
BUG-024
BUG-025
BUG-026
BUG-027
BUG-028
BUG-029
BUG-030
BUG-031
BUG-032
BUG-033
BUG-034
BUG-035
BUG-036
BUG-037
BUG-038
BUG-039
BUG-040
BUG-041
BUG-042
BUG-043
BUG-044
BUG-045
BUG-046
BUG-047
BUG-048
BUG-049
BUG-050

## Test Environment
TEST ENVIRONMENT DETAILS
Property | Development | Staging | Production
URL | http://localhost:3000
Framework | Next.js 15.5.12 | Next.js 15.5.12 | Next.js 15.5.12
Database | Supabase (PostgreSQL) | Supabase (PostgreSQL) | Supabase (PostgreSQL)
Authentication | Supabase Auth | Supabase Auth | Supabase Auth
Email Service | Resend API | Resend API | Resend API
Storage | Supabase Storage | Supabase Storage | Supabase Storage
Real-time | Supabase Realtime | Supabase Realtime | Supabase Realtime
Hosting | Local |  | Vercel
Node.js Version
Browser - Chrome
Browser - Firefox
Browser - Safari
Browser - Edge
Mobile - iOS Safari
Mobile - Android Chrome
Admin Email | bibaestore@gmail.com
Payment Methods | COD, Bank Transfer | COD, Bank Transfer | COD, Bank Transfer

## Sign-Off
QA TEST SIGN-OFF
Role | Name | Signature / Approval | Date | Comments
QA Lead
QA Tester 1
QA Tester 2
Developer Lead
Project Manager
Product Owner